Suggested Timeline

for Planning a Backyard Mission Project

| Step | Description | Time Frame |
| --- | --- | --- |
|  | ABCRM Church Transformation Team targets specific congregations to participate in BMP | 12 to 18 months prior weekend |
|  | Local church is invited to consider being a BMP host church | 6 to 9 months prior |
|  | Local church forms a BMP Team | 6 months prior |
|  | BMP Team works with community leaders to determine community needs | 5 months prior |
|  | BMP Team identifies three to four projects | 4 months prior |
|  | BMP Team writes descriptions of each project Materials and tools needed Anticipated cost of project Volunteers needed including identifying specific skills needed | 4 months prior |
|  | BMP Team prepares a preliminary budget Identify anticipated expenses Identify streams of income Set registration fees | 3 months prior |
|  | Church submits a proposal of projects to ABCRM staff and the Church Transformation Team | 3 months prior |
|  | BMP Team applies for Church Transformation Funds | 3 months prior |
|  | BMP Team invites other churches to participate | 3 months prior |
|  | ABCRM updates BMP Website | 3 months prior |
|  | Host pastor and ABCRM staff invite pastors to a meeting in the community to discuss the project and recruit support | 3 months prior |
|  | BMP Team prepare logistics plan Lodging Meals Insurance Schedule | 2 months prior |
|  | Recruit project coordinators | 2 months prior |
|  | ABCRM put articles in the Region newsletter requesting volunteers and describing projects | 2 months prior |
|  | Volunteer registration deadline | 1 month prior |
|  | Begin promoting in the community | 1 month prior |
|  | Project weekend |  |
|  | Post-project review | 1 month after |